|  | Odinsoft | Everhard Web site redesign |
| --- | --- | --- |
|  |  | eh-ccp10.doc |

Change Control Procedures

| Version | 1.1 |
| --- | --- |
| Date | 28/03/1999 |
| Status | Approved |
| Author(s) | Kirrilly Shipley |
| Editor | Darryl Lyons |
| Approved by | Darryl Lyons |
| # Approver’s Title | Project Manager |
| Approver’s Section |  |

About this Document

This document presents the standard procedure to be followed in the event that the client requests a change.

For more information about the procedures within this document contact Darryl Lyons (Project Manager) on (07) 3208 0213 or 0417 757 995.

This document was created using Microsoft Word.

Revision History

| Date | Version | Author(s) | Comments |
| --- | --- | --- | --- |
| 28/03/1999 | 1.1 | Darryl Lyons | Added one paragraph about risk management, changed the font sizes.. |

## Summary

As a project progresses it is usually inevitable that a client will request a change in order to improve the quality of the final product.  Changes in the early stages of the project can usually be easily factored into the schedule and project plan.  As the project progresses the impact of changes increases exponentially.  This produces the need to implement a strategy to manage change control and ensure the are reasonably executable.

This procedure is also tied closely with the Risk Management Plan, as client change requests can be considered risks to the project that could, and usually do arise.

## Procedure

- Client detects need/desire for change.

- Complete “Change Request Form”

- Forward to Project Manager

- Project Manager informs project team.  (may be more relevant to particular members)

- Impact is discussed and researched if necessary.

- Impact evaluated

- Decision on impact – if the change is feasible in regards to schedule etc

- Client informed of Decision.

- If negative decisions client is made aware of options/alternatives if appropriate.

- Client Considers and disregards or proposes change.

- Process is repeated.

PLEASE NOTE:

Step numbers 9,10 and 11 are not necessary if change is approved.  Appropriate changes are effected.